## Sheet1
ELMS — UAT Defect Log
System: Employee Leave Management System (ELMS) ¦ Target: UAT Test Execution (TC-001 to TC-029) ¦ Tester: Moshahed Ullah
TOTAL DEFECTS |  | OPEN DEFECTS |  |  | CRITICAL & HIGH |  |  | PENDING RETEST
4 |  | 3 |  |  | 1 |  |  | 4
Defect ID | Test Case ID | Defect Summary | Description | Severity | Priority | Status | Reported By | Assigned To | Resolution | Retest Result
DEF-001 | TC-006 | File upload backend storage not integrated | File selector opened in UI, but backend document upload storage is not integrated. Backend file storage API required. | Medium | Medium | Open | Moshahed Ullah | Backend Dev Team | Backend file storage API integration pending | Pending
DEF-002 | TC-010 | Email notification trigger failing due to missing SMTP relay | Email notification trigger cannot execute without live SMTP mail relay server. Workflow alerts blocked. | High | High | Open | Moshahed Ullah | Infrastructure Team | SMTP mail server integration pending | Pending
DEF-003 | TC-019 | Year-end batch rollover requires backend cron scheduler | Batch rollover script and encashment processing require backend server cron job execution. | Medium | Medium | Open | Moshahed Ullah | Backend Dev Team | Requires backend database scheduler / cron execution | Pending
DEF-004 | TC-029 | Power BI scheduled email export requires cloud workspace license | Direct PDF export works; automated scheduled email distribution requires Power BI Pro cloud tenant. | Low | Low | Deferred | Moshahed Ullah | BI / IT Admin | Cloud workspace tenant license required for scheduled subscriptions | Pending